PROJECT PROPOSAL

Intelligent Video Surveillance System for Hotel
Milestone XProtect + AI Analytics

Prepared by: IntelliForge
Client project: Hotel videovigilancia inteligente (Valencia)
Delivery mode: 100% Remote (no on-site visit required)
Date: August 2026

# 1. Executive Summary

This proposal covers the complete remote implementation and configuration of an intelligent video surveillance workflow for a hotel with 30 Safire Smart E1 Series cameras (already installed) and a Safire Smart B2 NVR (already operating). The core platform is Milestone XProtect, extended with AI analytics (BriefCam or equivalent) for facial recognition and multi line-crossing, plus real-time alerting to mobile and WhatsApp/SMS.

A interactive operator-workflow demo has already been prepared to illustrate live monitoring, watchlists, rules, alerts, search/reporting, and GDPR controls. The production delivery will be configured on the real Milestone/Safire environment (not a custom replacement VMS).

# 2. Project Understanding

Existing assets:

• 30× Safire Smart E1 Series cameras (Bullet/Turret 6MP) — installed

• Safire Smart B2 NVR — in operation

• Target platform: Milestone XProtect + AI analytics module

• Remote delivery preferred; no Valencia on-site visit required

Required functional outcomes:

• Facial recognition with employee / guest / blocked watchlists

• Multiple virtual line-crossing rules (room doors + common areas)

• Real-time alerts to mobile and WhatsApp/SMS

• Configurable rules (schedules + event combinations)

• Search and reports for suspicious events

• Easy PC operator interface (Milestone Smart Client)

• GDPR/AEPD-oriented configuration and documentation

• Remote training + 3–6 months post-deployment support

# 3. Project Scope

## 3.1 In Scope

• Remote audit of server/network/camera readiness and Milestone licensing status

• Milestone XProtect configuration (cameras, views, recording, users/roles)

• ONVIF integration/optimization for Safire Smart E1 cameras

• AI analytics configuration (facial watchlists + multi line-crossing)

• Milestone rules/alarms for schedules and combined events

• Alert path setup for App/mobile + WhatsApp/SMS via approved connector

• GDPR/AEPD baseline settings: retention, privacy masks, access roles

• Remote operator training sessions

• Technical documentation + end-user manual

• Post-go-live remote support (selected package)

## 3.2 Out of Scope

• Physical camera mounting / cabling (already installed)

• Purchase of Milestone / BriefCam / WhatsApp Business licenses (client-provided unless agreed otherwise)

• On-site travel to Valencia

• Development of a custom VMS to replace Milestone

• Legal GDPR advisory / DPO services (technical configuration + templates only)

# 4. Technology Stack

| Layer | Technology | Role in project |
| --- | --- | --- |
| VMS Core | Milestone XProtect | Central video management, recording, users, rules/alarms |
| Operator UI | XProtect Smart Client | Live view, playback, alarm handling on PC |
| Admin UI | XProtect Management Client | System configuration and rule setup |
| Cameras | Safire Smart E1 6MP (ONVIF) | Video sources (Bullet/Turret) |
| Edge/NVR | Safire Smart B2 NVR | Existing recording appliance / bridge as applicable |
| AI Analytics | BriefCam or equivalent | Facial recognition, watchlists, advanced search/events |
| Events/Rules | Milestone Rules + Alarm Manager | Schedules, combinations, severity routing |
| Mobile access | Milestone Mobile / Web (as licensed) | Remote monitoring for authorized staff |
| WhatsApp/SMS | WhatsApp Business API / SMS gateway (e.g. Twilio or approved provider) | Outbound critical alerts |
| Identity/Access | Milestone roles + Windows/AD if used | Admin / Security / Reception permissions |
| Compliance | Privacy masks, retention policies, audit logs | GDPR/AEPD technical controls |
| Docs & Demo | Technical manuals + workflow demo | Training aid and handover package |

Note: Facial recognition and WhatsApp are typically connected to Milestone (AI module + messaging connector), not native one-click features inside every XProtect edition. Final connector choice is confirmed in Phase 1.

# 5. Delivery Approach

• Phase-gated remote delivery with acceptance after each milestone

• Secure remote access (VPN/RDP) to Milestone server and camera network

• Configure first on a pilot set of cameras, then roll out to all 30

• Tune analytics to reduce false alarms before go-live

• Provide bilingual-ready operator guidance (ES/EN as needed)

• Keep production changes reversible and documented

# 6. Milestones, Timeline & Budget

Currency: EUR. Rate basis aligned with project posting (~€15/hour average). Total recommended go-live package: €2,100. Optional support packages listed below.

| Milestone | Duration | Key activities | Deliverables | Budget (EUR) |
| --- | --- | --- | --- | --- |
| M1 — Analysis & Kickoff | 4–5 days | Access check, license audit, network/camera health, GDPR requirements workshop | Audit report + implementation plan + risk list | 250 |
| M2 — Milestone Core Setup | 5–7 days | Camera onboarding (30), views/maps, recording profiles, users & roles | Configured XProtect environment ready for analytics | 550 |
| M3 — AI Analytics & Rules | 7–10 days | Watchlists, multi line-crossing, schedules, combined event rules | AI rules matrix + tuned detection profiles | 650 |
| M4 — Alerting (Mobile/WhatsApp/SMS) | 3–4 days | Alarm routing, connector setup, recipient matrix, escalation tests | Working alert path with test evidence | 300 |
| M5 — Testing & Optimization | 3–4 days | Scenario tests (night access, blocked list, door lines), false-alarm reduction | Test protocol + sign-off checklist | 200 |
| M6 — Training & Documentation | 2–3 days | Remote training for hotel staff, manuals, handover | User manual + technical docs + recorded session (optional) | 150 |

Go-live subtotal (M1–M6): €2,100

Estimated active delivery time to go-live: 5–6 weeks

## 6.1 Optional Support Packages

| Package | Period | Includes | Budget (EUR) |
| --- | --- | --- | --- |
| Support S3 | 3 months | Remote incident support, rule fine-tuning, monthly health check | 300 |
| Support S6 | 6 months | All S3 items + priority response + quarterly optimization review | 550 |

# 7. Payment Schedule

| Payment | When | Amount |
| --- | --- | --- |
| P1 | Contract start / after M1 kickoff acceptance | 20% (€420 of go-live) |
| P2 | After M2 + M3 acceptance | 40% (€840) |
| P3 | After M4 + M5 acceptance | 25% (€525) |
| P4 | After M6 training/docs acceptance (go-live) | 15% (€315) |
| Support | Monthly or upfront for selected support package | Per package |

# 8. Deliverables Checklist

☐ Milestone XProtect configured for hotel operations

☐ 30 cameras integrated and organized by floor/zone

☐ Facial watchlists configured (employees/guests/blocked)

☐ Virtual line-crossing rules for doors and common areas

☐ Alert workflow to mobile + WhatsApp/SMS (as approved)

☐ Role-based operator access (Admin / Security / Reception)

☐ GDPR-oriented technical settings and documentation pack

☐ Remote training completed

☐ Support handover package

# 9. Assumptions & Client Responsibilities

• Client provides remote admin access to Milestone server, NVR, and camera network

• Valid Milestone XProtect license/edition is available (or procurement is handled by client)

• AI analytics license (BriefCam or equivalent) is available, or approved as an add-on purchase

• WhatsApp Business / SMS provider account is available, or connector cost is approved

• Client nominates alert recipients and escalation contacts

• Client provides retention policy preferences and privacy-mask zones

• Network bandwidth and server hardware meet Milestone/AI vendor minimums

• Changes to scope (extra sites, extra analytics modules, custom development) may adjust budget/timeline

# 10. Risks & Mitigations

| Risk | Impact | Mitigation |
| --- | --- | --- |
| Missing AI/WhatsApp licenses | Delay on facial/WhatsApp features | Confirm in M1; provide fallback (SMS/email/mobile app) |
| High false alarms | Operator fatigue | Pilot tuning before full rollout; scheduled sensitivity reviews |
| Unstable remote access | Delivery slip | Dedicated VPN account + change window calendar |
| Camera ONVIF limitations | Partial analytics metadata | Validate per camera model in M1; use camera-side events where needed |

# 11. Demo Provided

An interactive workflow demo is available to show the intended operator experience (Introduction, Operations, Live view, Watchlists, Rules, Alerts, Search, GDPR, ES/EN). This demo is a simulation for clarification and training alignment. Production implementation is performed on Milestone XProtect with the hotel’s Safire infrastructure.

# 12. Why This Plan Works

• Matches the client’s required platform (Milestone-first, not a custom VMS rewrite)

• Clear milestones with fixed budgets and acceptance points

• Fully remote delivery (no Valencia travel cost/time)

• Includes compliance-minded configuration and staff enablement

• Support options protect the hotel after go-live

# 13. Acceptance

If this proposal is accepted, kickoff can start upon:

• Confirmation of selected package (Go-live only / +3 months / +6 months support)

• Remote access credentials

• License confirmation for Milestone + AI + messaging

• Signed milestone payment terms

Prepared by: IntelliForge

Project: Intelligent Hotel Video Surveillance — Milestone XProtect + AI Analytics

Total recommended investment: €2,400 (go-live + 3 months support)

Timeline to go-live: approximately 5–6 weeks (remote)